# SAEON Product Backlog

## Real Time Rainfall Monitoring System

The project follows 13 weekly sprints from 28 July to 23 October 2026, with work scheduled Tuesday to Friday. Planning, development, bench testing, documentation and presentation preparation are Completed. Final deployment, baseline field calibration and the 48-hour field validation activities remain In Progress.

| Product Backlog | In Progress | Completed |
| --- | --- | --- |
| Sprint 1: Project Initiation & System Architecture |  |  |
| Day 1: Define Project Scope & Board Setup |  | Completed |
| Day 2: Component Verification & Sourcing |  | Completed |
| Day 3: Development Environment Configuration |  | Completed |
| Day 4: Architecture Diagram & Data Flow |  | Completed |
| Sprint 2: Core Firmware & Sensor Interfacing |  |  |
| Day 1: ESP32 Base Setup & Serial Output |  | Completed |
| Day 2: DS18B20 Temperature Sensor Logic |  | Completed |
| Day 3: TR-525M Rain Gauge Logic |  | Completed |
| Day 4: Firmware Formatting & Low Power Mode |  | Completed |
| Sprint 3: HiveMQ Cloud Broker Setup |  |  |
| Day 1: Broker Provisioning |  | Completed |
| Day 2: Topic Structuring & Access Control |  | Completed |
| Day 3: Network Connection & Publish Testing |  | Completed |
| Day 4: Database Storage Integration |  | Completed |

# SAEON Product Backlog

Sprints 4 to 6

| Product Backlog | In Progress | Completed |
| --- | --- | --- |
| Sprint 4: Cellular Communication (SIM7000G) |  |  |
| Day 1: SIM Module Wiring & Power |  | Completed |
| Day 2: Network Bearer Configuration |  | Completed |
| Day 3: MQTT over Cellular |  | Completed |
| Day 4: Stability & Error Handling |  | Completed |
| Sprint 5: SAEON Dashboard Base Application |  |  |
| Day 1: App Skeleton & Routing |  | Completed |
| Day 2: Real-Time Visualization |  | Completed |
| Day 3: Historical Data & Filtering |  | Completed |
| Day 4: Cloud Command Prep |  | Completed |
| Sprint 6: Power Supply & Solar Integration |  |  |
| Day 1: Battery & Charge Controller Setup |  | Completed |
| Day 2: Solar Panel Integration |  | Completed |
| Day 3: Mains Power Alternative Testing |  | Completed |
| Day 4: System Power Flow Audit |  | Completed |

# SAEON Product Backlog

Sprints 7 to 9

| Product Backlog | In Progress | Completed |
| --- | --- | --- |
| Sprint 7: Advanced UI & Health Diagnostics |  |  |
| Day 1: Develop Station Health Diagnostics UI Component |  | Completed |
| Day 2: Implement CSV Export Functionality |  | Completed |
| Day 3: Mobile & Tablet Responsiveness |  | Completed |
| Day 4: Full End-to-End Data Pipeline Ping Test |  | Completed |
| Sprint 8: Hardware Finalization & PCB Soldering |  |  |
| Day 1: Circuit Transfer & Layout |  | Completed |
| Day 2: PCB Soldering |  | Completed |
| Day 3: Enclosure Preparation |  | Completed |
| Day 4: Component Mounting & Sealing |  | Completed |
| Sprint 9: Pre-Deployment Auditing & Calibration |  |  |
| Day 1: Power Drain Audit |  | Completed |
| Day 2: Solar Charging Verification |  | Completed |
| Day 3: Full System Deployment | In Progress |  |
| Day 4: Baseline Calibration | In Progress |  |

# SAEON Product Backlog

Sprints 10 to 12

| Product Backlog | In Progress | Completed |
| --- | --- | --- |
| Sprint 10: 48-Hour Field Stress Test |  |  |
| Day 1: Stress Test Initiation | In Progress |  |
| Day 2: Active Monitoring | In Progress |  |
| Day 3: Manual Field Measurements | In Progress |  |
| Day 4: Data Auditing & Conclusion | In Progress |  |
| Sprint 11: Presentation Formatting & Content |  |  |
| Day 1: Presentation Outlining |  | Completed |
| Day 2: Technical Diagrams & Architecture Slides |  | Completed |
| Day 3: Dashboard & Software Slides |  | Completed |
| Day 4: Technical Documentation |  | Completed |
| Sprint 12: Rehearsal & Submission Prep |  |  |
| Day 1: Slide Deck Finalization |  | Completed |
| Day 2: Group Rehearsal 1 |  | Completed |
| Day 3: Timed Rehearsal & Feedback |  | Completed |
| Day 4: Final Compilation |  | Completed |

# SAEON Product Backlog

Sprint 13

| Product Backlog | In Progress | Completed |
| --- | --- | --- |
| Sprint 13: Project Buffer & Final Review |  |  |
| Day 1-4: Buffer & Prototype Documentation Sign-off |  | Completed |

## Status and source notes

The statuses below reflect the project owner’s updates. Trello is the task-tracking board; GitHub stores code, documentation and evidence. The sprint backlog uses the same 13-sprint schedule and task statuses. These document updates do not modify the live Trello board.

Workflow: Product Backlog, In Progress and Completed. Sprint headings organise tasks and do not have completion marks. Sprint 13 sign-off covers the prototype documentation and presentation package; it is not final field-deployment acceptance. Supabase, historical data, CSV export, battery monitoring and solar integration are included in the current project scope.

Archived lists and archived cards are excluded. This product backlog shows sprint and daily card titles; individual checklist subtasks remain in Trello.

Source: SAEON Real-Time Rainfall Monitoring System Trello board export supplied by Ethan Williams.