# SAEON Rainfall Monitoring Sprint Backlog

ESP32 prototype with cellular MQTT and a live dashboard

This is the 13-week project plan for SAEON, running from 28 July to 23 October 2026 with work scheduled Tuesday to Friday. Each weekly sprint matches the product backlog and identifies its daily tasks, lead responsibilities, acceptance checks and current status.

The prototype counts TR-525M rain-gauge tips, reads a DS18B20 sensor through the ESP32 WROOM-32, and sends readings through the SIM7000G to HiveMQ Cloud. Supabase supports the dashboard, historical data and CSV export. Solar/battery integration and station health are included; final deployment and field validation remain In Progress.

## Team responsibilities

| Team member | Charter role | Backlog focus |
| --- | --- | --- |
| Redah Gamieldien | Project Leader | Requirements, hardware integration and final sign-off |
| Angelo Adams | Frontend Developer and Designer | Dashboard design and build, and making it easy to use |
| Qaasim Isaacs | Backend Developer and Tester | MQTT data handling, integration and test evidence |
| Ethan Williams | Analyst Researcher and Writer | Requirements, research and writing things up |
| Rameez Karriem | Agile Lead and Presenter | Planning, tracking tasks, running reviews and presenting |

## Working scope

The selected controller is ESP32 WROOM-32 and the selected temperature sensor is DS18B20. LilyGO and DHT11/SHT31 were earlier or exploratory options. The final communication route is SIM7000G cellular MQTT through HiveMQ Cloud, with Supabase for stored readings. Early HTTP/Firebase experiments are development history, not the final architecture.

The current scope includes solar charging, battery monitoring, station diagnostics, historical data, CSV export, authenticated dashboard access and permanent hardware assembly. Extra humidity, pressure, wind and UV sensors, GPS and over-the-air firmware updates remain future enhancements. Final field acceptance depends on site access, power, protection and completed validation.

## Planning basis

The 13 weekly sprints follow the current Trello-derived product backlog. Named leads coordinate tasks with the team; Ethan supports research and documentation across the project. Historical task estimates are not transferred to the revised schedule because the work breakdown has changed. Revised estimates and actual hours are not recorded.

# How we manage the backlog

There is one sprint backlog for each of the 13 project weeks. Statuses match the product backlog: 43 daily task cards are Completed and six deployment or field-validation cards are In Progress. These are project-owner updates, not independently verified test results.

## Weekly workflow

We plan weekly, check team capacity and use the agreed progress check-ins. Trello tracks tasks; GitHub stores code, documentation and evidence. Daily logbook entries are individual work notes and do not imply a formal stand-up meeting every day.

The shared task columns are Product Backlog, In Progress and Completed. Record any blocker, its owner and next action in the relevant task. Do not mark field work Completed until its acceptance evidence is available.

At the end of each sprint we demo what we built and write down any feedback from the lecturer or SAEON. Then we hold a short retrospective and pick one improvement to carry into the next sprint. Anything unfinished goes back to the product backlog so we can reprioritise it.

## Definition of Done

The task is finished and passes its acceptance checks, with the evidence linked on GitHub.

Someone else on the team has reviewed it and the relevant tests pass. Any defects or limits are written down.

The code, wiring diagrams, setup instructions and any other affected documents are updated.

The work meets the agreed rainfall, MQTT and dashboard requirements for that item.

The project leader signs it off and it is ready to demo or hand in.

## Sprint plan at a glance

| Week | Selected item | Focus | Est. hours |
| --- | --- | --- | --- |
| 1 | PB01 | Project Initiation & System Architecture | Not recorded |
| 2 | PB02 | Core Firmware & Sensor Interfacing | Not recorded |
| 3 | PB03 | HiveMQ Cloud Broker Setup | Not recorded |
| 4 | PB04 | Cellular Communication (SIM7000G) | Not recorded |
| 5 | PB05 | SAEON Dashboard Base Application | Not recorded |
| 6 | PB06 | Power Supply & Solar Integration | Not recorded |
| 7 | PB07 | Advanced UI & Health Diagnostics | Not recorded |
| 8 | PB08 | Hardware Finalization & PCB Soldering | Not recorded |
| 9 | PB09 | Pre-Deployment Auditing & Calibration | Not recorded |
| 10 | PB10 | 48-Hour Field Stress Test | Not recorded |
| 11 | PB11 | Presentation Formatting & Content | Not recorded |
| 12 | PB12 | Rehearsal & Submission Prep | Not recorded |
| 13 | PB13 | Project Buffer & Final Review | Not recorded |

The schedule below uses 13 workweeks. Earlier eight-week estimates have been superseded; revised person-hour estimates are not recorded. Calendar end dates are planning periods, not proof that all work finished within them.

# Product backlog

PB01 to PB13 map one-to-one to the 13 sprint groups in the product backlog. PB14 to PB16 record optional future enhancements. Story identifiers US01 to US13 refer to the separate User Stories and Tasks document and are not sprint numbers.

| ID | User story | Priority | When | Est. h |
| --- | --- | --- | --- | --- |
| PB01 | Project Initiation & System Architecture | Must | Week 1 | Not recorded |
| PB02 | Core Firmware & Sensor Interfacing | Must | Week 2 | Not recorded |
| PB03 | HiveMQ Cloud Broker Setup | Must | Week 3 | Not recorded |
| PB04 | Cellular Communication (SIM7000G) | Must | Week 4 | Not recorded |
| PB05 | SAEON Dashboard Base Application | Must | Week 5 | Not recorded |
| PB06 | Power Supply & Solar Integration | Must | Week 6 | Not recorded |
| PB07 | Advanced UI & Health Diagnostics | Must | Week 7 | Not recorded |
| PB08 | Hardware Finalization & PCB Soldering | Must | Week 8 | Not recorded |
| PB09 | Pre-Deployment Auditing & Calibration | Must | Week 9 | Not recorded |
| PB10 | 48-Hour Field Stress Test | Must | Week 10 | Not recorded |
| PB11 | Presentation Formatting & Content | Must | Week 11 | Not recorded |
| PB12 | Rehearsal & Submission Prep | Must | Week 12 | Not recorded |
| PB13 | Project Buffer & Final Review | Must | Week 13 | Not recorded |
| PB14 | Additional humidity, pressure, wind and UV sensing | Could | Future | Not recorded |
| PB15 | GPS location reporting | Could | Future | Not recorded |
| PB16 | Secure over-the-air firmware updates | Could | Future | Not recorded |

Must means required for the current agreed scope; Could identifies future enhancements. Revised estimates are Not recorded and are not commitments. Field work remains In Progress even though its original planned period has passed.

# Sprint 1: Project Initiation & System Architecture

Week 1  ·  28 July – 31 July 2026  ·  PB01  ·  Tuesday–Friday

Sprint goal  Agree the project scope, verify components, set up development tools and document the architecture.

Selected backlog item  PB01: Project Initiation & System Architecture. The daily task cards below match the product backlog.

Dependencies  Agreed scope, component access and team availability.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 1.01 | Day 1: Define Project Scope & Board Setup | Redah | Not recorded | Completed |
| 1.02 | Day 2: Component Verification & Sourcing | Redah | Not recorded | Completed |
| 1.03 | Day 3: Development Environment Configuration | Qaasim | Not recorded | Completed |
| 1.04 | Day 4: Architecture Diagram & Data Flow | Ethan | Not recorded | Completed |

## Acceptance criteria

Scope, roles, component choices and architecture are documented.

Trello and GitHub responsibilities are clear.

ESP32 WROOM-32 and DS18B20 are the selected controller and temperature sensor.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 2: Core Firmware & Sensor Interfacing

Week 2  ·  4 August – 7 August 2026  ·  PB02  ·  Tuesday–Friday

Sprint goal  Read temperature and rain-gauge tips on the ESP32 and prepare the firmware power behaviour.

Selected backlog item  PB02: Core Firmware & Sensor Interfacing. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–1, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 2.01 | Day 1: ESP32 Base Setup & Serial Output | Redah | Not recorded | Completed |
| 2.02 | Day 2: DS18B20 Temperature Sensor Logic | Redah | Not recorded | Completed |
| 2.03 | Day 3: TR-525M Rain Gauge Logic | Redah | Not recorded | Completed |
| 2.04 | Day 4: Firmware Formatting & Low Power Mode | Redah | Not recorded | Completed |

## Acceptance criteria

Controlled tips are counted once using a verified conversion factor.

Temperature readings and invalid-sensor states are identifiable.

Firmware formatting and low-power behaviour have recorded bench checks.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 3: HiveMQ Cloud Broker Setup

Week 3  ·  11 August – 14 August 2026  ·  PB03  ·  Tuesday–Friday

Sprint goal  Configure HiveMQ permissions, test MQTT delivery and connect Supabase storage.

Selected backlog item  PB03: HiveMQ Cloud Broker Setup. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–2, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 3.01 | Day 1: Broker Provisioning | Qaasim | Not recorded | Completed |
| 3.02 | Day 2: Topic Structuring & Access Control | Qaasim | Not recorded | Completed |
| 3.03 | Day 3: Network Connection & Publish Testing | Qaasim | Not recorded | Completed |
| 3.04 | Day 4: Database Storage Integration | Qaasim | Not recorded | Completed |

## Acceptance criteria

HiveMQ access uses documented publish and subscribe permissions.

Sample readings pass through the MQTT route securely.

Supabase stores station-linked, timestamped telemetry.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 4: Cellular Communication (SIM7000G)

Week 4  ·  18 August – 21 August 2026  ·  PB04  ·  Tuesday–Friday

Sprint goal  Send real readings through SIM7000G cellular MQTT and check connection stability.

Selected backlog item  PB04: Cellular Communication (SIM7000G). The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–3, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 4.01 | Day 1: SIM Module Wiring & Power | Redah | Not recorded | Completed |
| 4.02 | Day 2: Network Bearer Configuration | Qaasim | Not recorded | Completed |
| 4.03 | Day 3: MQTT over Cellular | Redah | Not recorded | Completed |
| 4.04 | Day 4: Stability & Error Handling | Qaasim | Not recorded | Completed |

## Acceptance criteria

Real messages reach the dashboard over cellular with Wi-Fi disabled.

Network registration and modem configuration are recorded.

Outage recovery and duplicate handling are checked.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 5: SAEON Dashboard Base Application

Week 5  ·  25 August – 28 August 2026  ·  PB05  ·  Tuesday–Friday

Sprint goal  Build the dashboard, live displays, historical filters and the interface for planned cloud commands.

Selected backlog item  PB05: SAEON Dashboard Base Application. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–4, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 5.01 | Day 1: App Skeleton & Routing | Angelo | Not recorded | Completed |
| 5.02 | Day 2: Real-Time Visualization | Angelo | Not recorded | Completed |
| 5.03 | Day 3: Historical Data & Filtering | Angelo | Not recorded | Completed |
| 5.04 | Day 4: Cloud Command Prep | Qaasim | Not recorded | Completed |

## Acceptance criteria

Current readings show units and latest update times.

Historical filters and data views work against stored records.

Cloud-command preparation is documented without claiming remote-control acceptance.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 6: Power Supply & Solar Integration

Week 6  ·  1 September – 4 September 2026  ·  PB06  ·  Tuesday–Friday

Sprint goal  Integrate battery and solar charging and verify the alternative power arrangement.

Selected backlog item  PB06: Power Supply & Solar Integration. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–5, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 6.01 | Day 1: Battery & Charge Controller Setup | Redah | Not recorded | Completed |
| 6.02 | Day 2: Solar Panel Integration | Redah | Not recorded | Completed |
| 6.03 | Day 3: Mains Power Alternative Testing | Qaasim | Not recorded | Completed |
| 6.04 | Day 4: System Power Flow Audit | Qaasim | Not recorded | Completed |

## Acceptance criteria

Battery and charging components are integrated and checked.

Solar and alternative power test results are recorded.

The power-flow audit records limitations.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 7: Advanced UI & Health Diagnostics

Week 7  ·  8 September – 11 September 2026  ·  PB07  ·  Tuesday–Friday

Sprint goal  Provide station diagnostics, CSV export, responsive views and an end-to-end pipeline check.

Selected backlog item  PB07: Advanced UI & Health Diagnostics. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–6, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 7.01 | Day 1: Develop Station Health Diagnostics UI Component | Angelo | Not recorded | Completed |
| 7.02 | Day 2: Implement CSV Export Functionality | Qaasim | Not recorded | Completed |
| 7.03 | Day 3: Mobile & Tablet Responsiveness | Angelo | Not recorded | Completed |
| 7.04 | Day 4: Full End-to-End Data Pipeline Ping Test | Qaasim | Not recorded | Completed |

## Acceptance criteria

Station health and stale-data states are visible.

CSV export matches the selected data.

Responsive views and the complete data path are checked.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 8: Hardware Finalization & PCB Soldering

Week 8  ·  15 September – 18 September 2026  ·  PB08  ·  Tuesday–Friday

Sprint goal  Transfer the prototype to its permanent circuit and mount it in the prepared enclosure.

Selected backlog item  PB08: Hardware Finalization & PCB Soldering. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–7, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 8.01 | Day 1: Circuit Transfer & Layout | Redah | Not recorded | Completed |
| 8.02 | Day 2: PCB Soldering | Redah | Not recorded | Completed |
| 8.03 | Day 3: Enclosure Preparation | Redah | Not recorded | Completed |
| 8.04 | Day 4: Component Mounting & Sealing | Redah | Not recorded | Completed |

## Acceptance criteria

The permanent circuit matches the reviewed wiring.

Soldering and mounting are checked.

The enclosure is prepared without treating assembly as field acceptance.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 9: Pre-Deployment Auditing & Calibration

Week 9  ·  22 September – 25 September 2026  ·  PB09  ·  Tuesday–Friday

Sprint goal  Audit power and charging, then proceed with installation and baseline field calibration.

Selected backlog item  PB09: Pre-Deployment Auditing & Calibration. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–8, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 9.01 | Day 1: Power Drain Audit | Qaasim | Not recorded | Completed |
| 9.02 | Day 2: Solar Charging Verification | Redah | Not recorded | Completed |
| 9.03 | Day 3: Full System Deployment | Redah | Not recorded | In Progress |
| 9.04 | Day 4: Baseline Calibration | Redah | Not recorded | In Progress |

## Acceptance criteria

Power drain and solar charging checks are Completed.

Installation and baseline field calibration remain In Progress.

Final site permission, protection and field records are required before acceptance.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 10: 48-Hour Field Stress Test

Week 10  ·  29 September – 2 October 2026  ·  PB10  ·  Tuesday–Friday

Sprint goal  Complete and audit the 48-hour field stress test; this field-validation work remains In Progress.

Selected backlog item  PB10: 48-Hour Field Stress Test. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–9, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 10.01 | Day 1: Stress Test Initiation | Qaasim | Not recorded | In Progress |
| 10.02 | Day 2: Active Monitoring | Qaasim | Not recorded | In Progress |
| 10.03 | Day 3: Manual Field Measurements | Ethan | Not recorded | In Progress |
| 10.04 | Day 4: Data Auditing & Conclusion | Ethan | Not recorded | In Progress |

## Acceptance criteria

The test duration, uptime and delivery gaps are recorded when available.

Reference measurements and timestamps can be compared.

Field conclusions are not marked Completed before the test and audit finish.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 11: Presentation Formatting & Content

Week 11  ·  6 October – 9 October 2026  ·  PB11  ·  Tuesday–Friday

Sprint goal  Complete presentation content, diagrams, dashboard evidence and technical documentation.

Selected backlog item  PB11: Presentation Formatting & Content. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–10, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 11.01 | Day 1: Presentation Outlining | Ethan | Not recorded | Completed |
| 11.02 | Day 2: Technical Diagrams & Architecture Slides | Ethan | Not recorded | Completed |
| 11.03 | Day 3: Dashboard & Software Slides | Ethan | Not recorded | Completed |
| 11.04 | Day 4: Technical Documentation | Ethan | Not recorded | Completed |

## Acceptance criteria

Slides describe the actual architecture and current results.

The setup guide and technical documentation are complete for the prototype.

Open field-validation limitations are explicit.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 12: Rehearsal & Submission Prep

Week 12  ·  13 October – 16 October 2026  ·  PB12  ·  Tuesday–Friday

Sprint goal  Finalise the slides, rehearse the demonstration and compile the prototype submission materials.

Selected backlog item  PB12: Rehearsal & Submission Prep. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–11, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 12.01 | Day 1: Slide Deck Finalization | Ethan | Not recorded | Completed |
| 12.02 | Day 2: Group Rehearsal 1 | Rameez | Not recorded | Completed |
| 12.03 | Day 3: Timed Rehearsal & Feedback | Rameez | Not recorded | Completed |
| 12.04 | Day 4: Final Compilation | Rameez | Not recorded | Completed |

## Acceptance criteria

Speaking parts and rehearsals are prepared.

A backup demonstration and submission package are compiled.

Preparation does not imply a submission receipt or final field approval.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Sprint 13: Project Buffer & Final Review

Week 13  ·  20 October – 23 October 2026  ·  PB13  ·  Tuesday–Friday

Sprint goal  Review the prototype documentation package and record outstanding deployment work separately.

Selected backlog item  PB13: Project Buffer & Final Review. The daily task cards below match the product backlog.

Dependencies  Relevant outputs from Sprints 1–12, team capacity and required equipment or services.

## Sprint tasks

| Task ID | Task and expected output | Lead | Est. h | Status |
| --- | --- | --- | --- | --- |
| 13.01 | Day 1-4: Buffer & Prototype Documentation Sign-off | Redah | Not recorded | Completed |

## Acceptance criteria

The prototype documentation and presentation package are reviewed.

The deployment and field-validation actions remain open.

Prototype sign-off is distinguished from field-deployment acceptance.

Review evidence  Linked task outputs, configuration or wiring records, screenshots, logs and review notes as applicable. No deployment acceptance or submission receipt is inferred.

| Review date: Not recorded |  |
| --- | --- |
| Review notes: Record actual evidence and feedback; field work remains open where marked In Progress. | Retrospective: Record the team’s actual improvement actions; no dated meeting outcome supplied. |

# Release and handover

## Release review checklist

Show real rain tips and temperature readings arriving on the live dashboard through cellular MQTT.

Show bench calibration, recorded test results, message-delivery evidence and outage handling. Clearly separate these from the In Progress baseline field calibration and 48-hour validation.

Confirm that the tagged code, wiring guide and setup instructions rebuild the prototype that was assessed.

Record the known limitations, the extras we postponed and the feedback from the lecturer or SAEON.

Prototype documentation sign-off is Completed. Final field-deployment acceptance remains open until installation, baseline calibration and field validation are complete. Retain an actual submission receipt only when a submission is made.

## Supporting project documents

Agile Team Charter SAEON Rainfall Monitoring: team roles, 13-week milestones, working agreements and Definition of Done.

SAEON ESP32 Rainfall Monitoring Basic Presentation. Where we got the problem, who benefits, the core hardware and the cellular MQTT data flow.

SAEON Project Sprint Plan. Our reference for task ideas, sensor integration, communication tests and handover activities.